## Sheet1
Sr No | Task | Target Date | Status
1 | Requrirement gathering |  | Done
2 | Database using Django model |  | Done
3 | Updating master with unique records |  | Done
4 | Updating historical data using ETL | 2019-09-06 | Done
5 | Finding CIK using name of the companies | 2019-09-10 | Pending
6 | Downloading 10K, 10Q filling | 2019-09-16 | Pending
7 | generating Credit score | 2019-09-23 | Pending
8 | Calculate weightage based on the credit score | 2019-09-25 | Pending
9 | Update database table for calculated weight. | 2019-09-26 | Pending
10 | Plotting graph | 2019-09-30 | Pending